## Implemetation plan
EBPS / CNAPS renewal cetirifcate CHG1909315
Type | Task No. | Start Time (HKT) | End Time (HKT) | Duration (hh:mm) | Actual (hh:mm) | Task / Activity | Owner | Maker | Checker | Comments | GSD Group | Completed (Remarks) | Act. Start | Act. End | Spent | Remark
| 1 | 2023-08-27 09:00 | 2023-08-27 09:05 | 0:05 |  | GPS task -hold all outward domestic payments in Mfilter during period | GPE | Jawn Z J WU | Penn peng / Ray ji | update syst_par set parm_value='Yes' where param_name='TYPHOONIND'; --Apply cache /opt/gppcnp/gpp/tools/tasks/Ctrl-M-Plus-encrypted.ksh wallet:GPSCNAP_TAF_WAL ALL "Apply Changes (Refresh Internal Cache)" APPLY SINGLE |  |  | 9:00 | 9:04
| 2 | 2023-08-27 09:05 | 2023-08-27 09:10 | 0:05 |  | Logoff CNAPS system | OPS | Kevin C SUN | Charles shi |  |  |  | 9:04 | 9:07
|  | 2023-08-27 09:10 | 2023-08-27 09:15 | 0:05 |  | Backup CNAPS Old certificate | SWD | Vendor | Penn peng / Ray ji |  |  |  | 9:05 | 9:07
| 3 | 2023-08-27 09:15 | 2023-08-27 09:35 | 0:20 |  | CNAPS certificate renew task | SWD | Vendor | Penn peng / Ray ji |  |  |  | 9:08 | 9:18
| 4 | 2023-08-27 09:35 | 2023-08-27 09:43 | 0:08 |  | application health check | OPS | Kevin C SUN | Charles shi |  |  |  | 9:19 | 9:26
| 5 | 2023-08-27 09:43 | 2023-08-27 09:48 | 0:05 |  | Logon CNAPS system | OPS | Kevin C SUN | Charles shi |  |  |  | 9:27 | 9:28
| 6 | 2023-08-27 09:48 | 2023-08-27 09:50 | 0:02 |  | Logoff EBPS system | SWD | Penn peng / Sunny | Ray ji | select bankcode, case STATE WHEN 'US01' THEN 0 WHEN 'US00' THEN 1 WHEN 'SP00' THEN 1 WHEN 'SP03' THEN 1 WHEN 'SP01' THEN 0 WHEN 'SP02' THEN 0 END AS status from T_USI_PFBANKINF where state in ('US00','SP00','SP03') order by bankcode; |  |  | 9:29 | 9:30
| 7 | 2023-08-27 09:50 | 2023-08-27 09:55 | 0:05 |  | Backup EBPS Old certificate | SWD | Vendor | Penn peng / Ray ji |  |  |  | 9:30 | 9:32
| 8 | 2023-08-27 09:55 | 2023-08-27 10:15 | 0:20 |  | EBPS application renew Certificate | SWD | Vendor | Penn peng / Ray ji |  |  |  | 9:32 | 9:43
| 9 | 2023-08-27 10:15 | 2023-08-27 10:23 | 0:08 |  | application health check | swd | Penn peng / Sunny | Ray ji |  |  |  | 9:43 | 9:53
| 10 | 2023-08-27 10:23 | 2023-08-27 10:25 | 0:02 |  | Logon EBPS system | SWD | Penn peng / Sunny | Ray ji | select bankcode, case STATE WHEN 'US01' THEN 0 WHEN 'US00' THEN 1 WHEN 'SP00' THEN 1 WHEN 'SP03' THEN 1 WHEN 'SP01' THEN 0 WHEN 'SP02' THEN 0 END AS status from T_USI_PFBANKINF where state in ('US00','SP00','SP03') order by bankcode; |  |  | 9:53 | 9:54
|  | 2023-08-27 10:25 | 2023-08-27 10:45 | 0:20 |  | CNAPS and EBPS it an ops health check | SWD/OPS | Penn peng / Sunny/Kevin C SUN | Ray ji Charles shi
| 11 | 2023-08-27 10:45 | 2023-08-27 10:50 | 0:05 |  | Restore setup in GPS to release outward payment | GPE | Jawn Z J WU | Penn peng / Ray ji | update syst_par set parm_value='NO' where param_name='TYPHOONIND'; --Apply cache /opt/gppcnp/gpp/tools/tasks/Ctrl-M-Plus-encrypted.ksh wallet:GPSCNAP_TAF_WAL ALL "Apply Changes (Refresh Internal Cache)" APPLY SINGLE |  |  | 9:55 | 9:58
Formulas:
End Time (HKT) = [Start Time (HKT)]+[Duration (hh:mm)]
End Time (HKT) = [Duration (hh:mm)]+[Start Time (HKT)]
Start Time (HKT) = [End Time (HKT), row above]

## Backout
EBPS / CNAPS renewal cetirifcate CHG1909315
Type | Task No. | Start Time (HKT) | End Time (HKT) | Duration (hh:mm) | Actual (hh:mm) | Task / Activity | Owner | Maker | Checker | Comments | GSD Group | Completed (Remarks) | Act. Start | Act. End | Spent | Remark
| 1 | 2023-08-27 10:50 | 2023-08-27 10:55 | 0:05 |  | GPS task -hold all outward domestic payments in Mfilter during period | GPE | Jawn Z J WU | Penn peng / Ray ji | update syst_par set parm_value='Yes' where param_name='TYPHOONIND'; --Apply cache /opt/gppcnp/gpp/tools/tasks/Ctrl-M-Plus-encrypted.ksh wallet:GPSCNAP_TAF_WAL ALL "Apply Changes (Refresh Internal Cache)" APPLY SINGLE
| 2 | 2023-08-27 10:55 | 2023-08-27 11:00 | 0:05 |  | Logoff CNAPS system | OPS | Kevin C SUN | Charles shi
|  | 2023-08-27 11:00 | 2023-08-27 11:05 | 0:05 |  | Fallback CNAPS Old certificate | SWD | Vendor | Penn peng / Ray ji
| 4 | 2023-08-27 11:05 | 2023-08-27 11:15 | 0:10 |  | application health check | OPS | Kevin C SUN | Charles shi
| 5 | 2023-08-27 11:15 | 2023-08-27 11:20 | 0:05 |  | Logon CNAPS system | OPS | Kevin C SUN | Charles shi
| 6 | 2023-08-27 11:20 | 2023-08-27 11:22 | 0:02 |  | Logoff EBPS system | SWD | Penn peng / Sunny | Ray ji | select bankcode, case STATE WHEN 'US01' THEN 0 WHEN 'US00' THEN 1 WHEN 'SP00' THEN 1 WHEN 'SP03' THEN 1 WHEN 'SP01' THEN 0 WHEN 'SP02' THEN 0 END AS status from T_USI_PFBANKINF where state in ('US00','SP00','SP03') order by bankcode;
| 7 | 2023-08-27 11:22 | 2023-08-27 11:27 | 0:05 |  | Fallback EBPS Old certificate | SWD | Vendor | Penn peng / Ray ji
| 9 | 2023-08-27 11:27 | 2023-08-27 11:37 | 0:10 |  | application health check | swd | Penn peng / Sunny | Ray ji
| 10 | 2023-08-27 11:37 | 2023-08-27 11:40 | 0:03 |  | Logon EBPS system | SWD | Penn peng / Sunny | Ray ji | select bankcode, case STATE WHEN 'US01' THEN 0 WHEN 'US00' THEN 1 WHEN 'SP00' THEN 1 WHEN 'SP03' THEN 1 WHEN 'SP01' THEN 0 WHEN 'SP02' THEN 0 END AS status from T_USI_PFBANKINF where state in ('US00','SP00','SP03') order by bankcode;
| 11 | 2023-08-27 11:40 | 2023-08-27 11:45 | 0:05 |  | Restore setup in GPS to release outward payment | GPE | Jawn Z J WU | Penn peng / Ray ji | update syst_par set parm_value='NO' where param_name='TYPHOONIND'; --Apply cache /opt/gppcnp/gpp/tools/tasks/Ctrl-M-Plus-encrypted.ksh wallet:GPSCNAP_TAF_WAL ALL "Apply Changes (Refresh Internal Cache)" APPLY SINGLE
Formulas:
End Time (HKT) = [Start Time (HKT)]+[Duration (hh:mm)]
End Time (HKT) = [Duration (hh:mm)]+[Start Time (HKT)]
Start Time (HKT) = [End Time (HKT), row above]

## Contact
Team | Contact | Support Location | Support Mobile | support windows
SWD Payment team | Karl Wu | 08/27 09:00 - 12:00 Remote | 13621766495 | 08/27 09:00 - 12:00 Remote
SWD Payment team | Sunny z h huang hellen q he | 08/27 09:00 - 12:00 Remote |  | 08/27 09:00 - 12:00 Remote
SWD Payment team | Ray ji (Local)/PENG penn | 08/27 09:00 - 12:00 Remote | Ray:13761138444 Local Penn:18813294980 | 08/27 09:00 - 12:00 Remote
GPS team | Jawn z j wu | 08/27 09:00 - 12:00 Remote | Jawn z j wu:15298940152 | 08/27 09:00 - 12:00 Remote
Ylink team | Gu:13651914473 Bi:17621179395 Shuai Ma:15275196791 | 08/27 09:00 - 12:00 Remote | Gu:13651914473 Bi:17621179395 Shuai Ma:15275196791 | 08/27 09:00 - 12:00 Remote
信安世纪 | 蔡磊/戴凌峰 | 08/27 09:00 - 12:00 Local | 蔡磊:17301653994 戴凌峰:13524205833 | 08/27 09:00 - 12:00 Local
OPS | Charle shi | 08/27 09:00 - 12:00 Remote | charle:13585964800 | 08/27 09:00 - 12:00 Remote